## Dashboard
REALTOUCH FINANCIAL ERP — COMPLIANCE READINESS TRACKER
Harvest Touch Youth & Skills Community Hub CIC ¦ Based on Compliance Audit Report April 2026
Prepared by: Realtouch Research & Consulting ¦ CFO: Dominic Ogbuagu | [6 empty] | Last Updated: 13 April 2026
OVERALL COMPLIANCE READINESS
Financial Accounting |  |  |  | HMRC Payroll |  |  |  | HR Compliance
P1. Core |  |  |  | P1. Core |  |  |  | P1. Critical
UKVI Sponsorship |  |  |  | GDPR / Data Protection |  |  |  | Charity Commission/CIC
P3. Medium |  |  |  | P1. Critical |  |  |  | P2. High
Data Security |  |  |  | Grant Management |  |  |  | Donation Management
P2. High |  |  |  | P1. Core |  |  |  | P2. High
COMPLIANCE DOMAIN SUMMARY
Domain | Priority | Total Items | Completed | In Progress | Not Started | % Complete | Status | Target Date
Financial Accounting | P1 — Critical | [6 empty] | Mar 2026
HMRC Payroll | P1 — Critical | [6 empty] | Mar 2026
HR Compliance | P1 — Critical | [6 empty] | Apr 2026
GDPR / Data Protection | P1 — Critical | [6 empty] | Apr 2026
Charity Commission/CIC | P2 — High | [6 empty] | May 2026
Data Security | P2 — High | [6 empty] | Apr 2026
Grant Management | P1 — Core ✓ | [6 empty] | Mar 2026
Donation Management | P2 — High | [6 empty] | Apr 2026
UKVI Sponsorship | P3 — Medium | [6 empty] | Jun 2026
TOTAL | [6 empty] | OVERALL
KEY — STATUS DEFINITIONS
✅ Complete | Implementation done, tested in production, evidence documented
🔄 In Progress | Development started — code written, partial implementation
⬜ Not Started | Not yet begun — identified as required, awaiting development

## P1_Financial
FINANCIAL ACCOUNTING — COMPLIANCE CHECKLIST
Core accounting engine, fund accounting, SORP compliance, year-end close, and statutory reporting
Regulatory Basis: FRS 102 · Charities SORP · Charity Commission · HMRC
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
FA-01 | Accounting Engine | Double-entry bookkeeping enforced | Every journal entry must balance — debits must equal credits. Validation exists in journal-entry endpoint. | ✅ Complete | Tech Lead | Live | Test results + code review |  | Implemented and tested
FA-02 | Accounting Engine | Chart of accounts (5 account types) | Asset, Liability, Equity, Income, Expense account types with code and name | ✅ Complete | Tech Lead | Live | Code review |  | Full chart in seed data
FA-03 | Accounting Engine | Journal entries with reference numbering | Sequenced reference (JE-2025-0001) and status tracking (draft/posted/voided) | ✅ Complete | Tech Lead | Live | Code review
FA-04 | Accounting Engine | Grant-coded transactions | Every transaction and journal line tagged with grant_id and programme_id | ✅ Complete | Tech Lead | Live | Code review |  | Essential for funder reporting
FA-05 | Bank Reconciliation | Bank account model | Bank accounts, sort codes, balances modelled in database | ✅ Complete | Tech Lead | Live | Code review
FA-06 | Bank Reconciliation | Bank reconciliation workflow | UI and API for matching bank transactions to journal entries | 🔄 In Progress | Tech Lead | Apr 2026 | Functional testing |  | Manual matching only — no auto-match
FA-07 | Bank Reconciliation | Period lock after reconciliation | Prevent posting transactions on or before a reconciled lock date | ⬜ Not Started | Tech Lead | May 2026 | Testing + audit trail evidence |  | Add lock_date field to BankAccount model
FA-08 | Fund Accounting | Restricted fund tracking | Separate Fund model with fund_type: restricted/unrestricted/endowment | ⬜ Not Started | Tech Lead | Apr 2026 | Charity Commission SORP compliance test |  | CRITICAL for grant-funded CIC — required by Charities SORP
FA-09 | Fund Accounting | Fund_id on all transactions | Every transaction, journal line, and expense tagged with fund_id | ⬜ Not Started | Tech Lead | Apr 2026 | Data model review |  | Depends on FA-08
FA-10 | Statutory Reporting | Statement of Financial Activities (SoFA) | SORP-compliant SoFA grouping income/expenditure by fund type | ⬜ Not Started | Tech Lead | May 2026 | Accountant sign-off |  | Required for Charity Commission annual return
FA-11 | Statutory Reporting | Balance Sheet in FRS 102 format | Assets, liabilities, net assets in UK GAAP / FRS 102 format | ⬜ Not Started | CFO | May 2026 | Independent examiner review
FA-12 | Statutory Reporting | Year-end close process | Ability to lock a financial year, carry forward balances, produce trial balance | ⬜ Not Started | Tech Lead | Jun 2026 | Audit test |  | Required before independent examiner can sign off
FA-13 | Statutory Reporting | Dormant account detection | Flag accounts with zero movement for 12+ months in reporting | ⬜ Not Started | Tech Lead | Jun 2026 | Code review |  | Best practice for audit cleanliness
FA-14 | VAT | VAT return model | VAT period, output/input VAT, net VAT, MTD submission reference | ⬜ Not Started | Tech Lead | Jul 2026 | HMRC VAT portal test |  | May not apply to HT now — build for multi-tenant SaaS
FA-15 | VAT | Making Tax Digital (MTD) integration | API integration with HMRC MTD endpoint for digital VAT submission | ⬜ Not Started | Tech Lead | Sep 2026 | HMRC MTD sandbox test |  | Required if turnover exceeds £90k
FA-16 | Related Parties | Related party transaction disclosure | Record and flag any financial transactions with trustees or connected persons | ⬜ Not Started | CFO | Jun 2026 | Charity Commission guidance CC29 |  | Required disclosure in annual accounts

## P1_Payroll
HMRC PAYROLL COMPLIANCE — COMPLIANCE CHECKLIST
PAYE, NI, pension, RTI filing, statutory documents (P60/P45/P11D), NMW validation, SSP/SMP
Regulatory Basis: HMRC PAYE · Employment Rights Act 1996 · National Minimum Wage Act 1998 · The Pensions Regulator
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
PR-01 | PAYE | Income Tax calculation (2024-25) | Personal allowance £12,570, basic 20%, higher 40%, additional 45% | ✅ Complete | Tech Lead | Live | Test results (52/52 passing) |  | All rates verified in test suite
PR-02 | National Insurance | Employee NI Class 1 (8%/2%) | Primary threshold £12,570, UEL £50,270, main rate 8%, upper 2% | ✅ Complete | Tech Lead | Live | Test results |  | 2024-25 rates correct
PR-03 | National Insurance | Employer NI (13.8%) | Secondary threshold £9,100, 13.8% above threshold | ✅ Complete | Tech Lead | Live | Test results
PR-04 | Pension | Auto-enrolment pension calculation | Qualifying earnings £6,240–£50,270, employee 5%, employer 3% | ✅ Complete | Tech Lead | Live | Test results |  | AE thresholds correct
PR-05 | Pension | Student loan deductions (Plan 2) | Threshold £27,295, rate 9% | ✅ Complete | Tech Lead | Live | Test results
PR-06 | Payslips | PDF payslip generation | ReportLab PDF with all statutory fields | ✅ Complete | Tech Lead | Live | Sample payslip review
PR-07 | Payslips | Payslip email delivery | Email service sends payslip PDF to employee email | ✅ Complete | Tech Lead | Live | Email delivery test
PR-08 | NMW | National Minimum Wage validation | Validate gross_salary / contracted_hours >= applicable NMW tier before payroll run confirms | ⬜ Not Started | Tech Lead | URGENT | NMW compliance test — no payroll run should complete below NMW |  | CRIMINAL LIABILITY — highest priority item in entire system
PR-09 | RTI | RTI submission tracking flag | rti_submitted boolean on PayrollRun — tracks submission status | ✅ Complete | Tech Lead | Live | Code review |  | Flag only — not actual submission
PR-10 | RTI | HMRC Government Gateway RTI filing | Actual electronic RTI FPS/EPS submission to HMRC via API | ⬜ Not Started | Tech Lead | Jun 2026 | HMRC sandbox test confirmation |  | Required for legal compliance — manual submission via HMRC Basic PAYE Tools acceptable interim
PR-11 | Year-End Documents | P60 generation (year-end certificate) | P60 PDF for every employee by 31 May — total gross, PAYE, NI for tax year | ⬜ Not Started | Tech Lead | Mar 2026 | P60 sample review by accountant |  | LEGAL REQUIREMENT — every employee by 31 May
PR-12 | Year-End Documents | P45 generation (leaver document) | P45 PDF on employee termination — Parts 1, 1A, 2, 3 | ⬜ Not Started | Tech Lead | Apr 2026 | P45 sample review |  | LEGAL REQUIREMENT on leaving
PR-13 | Benefits | P11D (benefits in kind declaration) | P11D model + PDF for any employee receiving non-cash benefits | ⬜ Not Started | Tech Lead | May 2026 | P11D sample + accountant review |  | Required if any benefit is provided
PR-14 | Off-Payroll | IR35 assessment tool | Assessment model for contractor engagements with CEST reference | ⬜ Not Started | CFO | Jun 2026 | Legal counsel sign-off on tool |  | Required for any sessional / freelance workers
PR-15 | YTD Totals | Cumulative YTD payroll totals | ytd_gross, ytd_tax, ytd_ni populated correctly on every PayrollRecord | ⬜ Not Started | Tech Lead | Apr 2026 | YTD test across 3 months |  | Currently fields exist but are never populated — breaks P60
PR-16 | Statutory Pay | Statutory Sick Pay (SSP) calculation | SSP £116.75/wk (2024-25), qualifying days, 28-week maximum | ⬜ Not Started | Tech Lead | May 2026 | SSP test scenario
PR-17 | Statutory Pay | Statutory Maternity Pay (SMP) | 90% AWE first 6 weeks, then £184.03/wk | ⬜ Not Started | Tech Lead | May 2026 | SMP test scenario
PR-18 | Statutory Pay | Statutory Paternity Pay (SPP) | 2 weeks at £184.03/wk | ⬜ Not Started | Tech Lead | May 2026 | SPP test scenario
PR-19 | Pension | Pension re-enrolment (triennial) | Re-enrol eligible workers every 3 years — Celery task with alert | ⬜ Not Started | Tech Lead | Jun 2026 | Re-enrolment test |  | Pensions Regulator requirement
PR-20 | Making Tax Digital | MTD PAYE integration | Digital PAYE / Income Tax submissions (MTD for ITSA from 2026) | ⬜ Not Started | Tech Lead | Dec 2026 | HMRC MTD sandbox test |  | Plan ahead — mandatory from April 2026 for some

## P2_HR
HR COMPLIANCE — COMPLIANCE CHECKLIST
Right to Work, DBS checks, safeguarding, leave management, disciplinary, equality monitoring
Regulatory Basis: Employment Rights Act 1996 · Children Act 1989/2004 · Equality Act 2010 · Working Time Regulations 1998 · ACAS Code
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
HR-01 | Right to Work | Right to Work verification record | Date checked, document type, number, expiry, recheck date per employee | ⬜ Not Started | HR Manager | URGENT | Evidence document scans + check dates |  | CRIMINAL LIABILITY — illegal working offence
HR-02 | Right to Work | Right to Work expiry alerts | Celery task: alert 90, 60, 30 days before document expiry | ⬜ Not Started | Tech Lead | Mar 2026 | Alert email test
HR-03 | DBS Checks | DBS check record per staff member | Certificate number, type (basic/standard/enhanced+barred), issue date, expiry | ⬜ Not Started | HR Manager | URGENT | DBS certificate copies on file |  | MANDATORY for youth organisation — safeguarding duty
HR-04 | DBS Checks | DBS expiry alerts | Celery task: alert 90, 30 days before renewal | ⬜ Not Started | Tech Lead | Mar 2026 | Alert email test
HR-05 | DBS Checks | DBS records for volunteers | All volunteers working with young people require enhanced DBS | ⬜ Not Started | HR Manager | URGENT | Volunteer DBS records |  | Same legal requirement as employees for regulated activities
HR-06 | Safeguarding | Safeguarding training records | Training type, completion date, expiry, provider per staff member and volunteer | ⬜ Not Started | HR Manager | Mar 2026 | Training certificates |  | Statutory duty under Children Act 1989/2004
HR-07 | Safeguarding | Safeguarding policy compliance status | Dashboard showing all staff/volunteers with expired or upcoming renewal | ⬜ Not Started | Tech Lead | Apr 2026 | Functional test |  | Required for Ofsted and any CQC inspection
HR-08 | Leave Management | Annual leave entitlement tracking | 28 days FT statutory minimum — accrual, balance, requests, approvals | ⬜ Not Started | Tech Lead | May 2026 | Leave balance accuracy test |  | Working Time Regulations 1998
HR-09 | Leave Management | Sick leave and absence records | Absence type, duration, SSP trigger, return-to-work record | ⬜ Not Started | Tech Lead | May 2026 | SSP linkage test |  | Required for SSP calculation
HR-10 | Leave Management | Maternity / paternity leave records | Leave dates, SMP/SPP calculation link, return-to-work date | ⬜ Not Started | Tech Lead | May 2026 | SMP/SPP test
HR-11 | Contracts | Employment contract storage | Signed contract document upload and version tracking per employee | ⬜ Not Started | HR Manager | Apr 2026 | Contract file for every active employee |  | Employment Rights Act 1996 — written statement within 2 months
HR-12 | Probation | Probation period tracking | Start date, duration, review dates, outcome (passed/extended/failed) | ⬜ Not Started | HR Manager | May 2026 | Probation records
HR-13 | Disciplinary | Disciplinary case records | Case type, opened date, outcome, appeal, confidential flag | ⬜ Not Started | HR Manager | May 2026 | ACAS Code of Practice compliance |  | Employment Rights Act 1996 — required to defend tribunal claims
HR-14 | Disciplinary | Grievance records | Grievance type, dates, outcome, resolution | ⬜ Not Started | HR Manager | May 2026 | ACAS Code of Practice compliance
HR-15 | Equality | Equality and diversity monitoring | Voluntary anonymised monitoring — protected characteristics under Equality Act 2010 | ⬜ Not Started | HR Manager | Jun 2026 | Diversity report sample |  | Required for grant funder compliance and public sector equality duty
HR-16 | Training | CPD and training records | Training type, date, provider, certification — per staff member | ⬜ Not Started | HR Manager | May 2026 | Training log |  | Required for evidence in grant reports
HR-17 | Volunteer Management | Volunteer agreement recording | Signed volunteer agreement date, induction date, role description | ⬜ Not Started | HR Manager | Apr 2026 | Volunteer agreement files
HR-18 | Working Time | Working Time Regulations compliance | 48-hour opt-out recording, rest break tracking for irregular hours workers | ⬜ Not Started | HR Manager | Jun 2026 | WTR audit evidence |  | Working Time Regulations 1998
HR-19 | Whistleblowing | Whistleblowing policy reference and case log | Policy version, case reference, nature, resolution, legal protection flag | ⬜ Not Started | HR Manager | Jun 2026 | Public Interest Disclosure Act 1998 compliance

## P2_GDPR
GDPR / DATA PROTECTION — COMPLIANCE CHECKLIST
UK GDPR / DPA 2018 compliance — consent, data subject rights, retention, encryption, breach logging
Regulatory Basis: UK GDPR · Data Protection Act 2018 · ICO Accountability Framework
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
DP-01 | Consent Management | Lawful basis recording for each data category | Article 6 GDPR — record lawful basis (consent/contract/legal obligation/legitimate interest) per data type | ⬜ Not Started | DPO / CFO | Apr 2026 | ICO accountability framework checklist |  | Required for every category of personal data processed
DP-02 | Consent Management | Donor marketing consent | Consent date, method (online/paper), withdrawal date, version of privacy notice | ⬜ Not Started | Tech Lead | Apr 2026 | Consent audit trail |  | GDPR Article 7 — consent must be freely given, specific, informed
DP-03 | Consent Management | Gift Aid declaration evidence | Donor declaration date, declaration method, declaration text version | 🔄 In Progress | Tech Lead | Apr 2026 | Gift Aid audit trail |  | gift_aid_eligible boolean exists — needs date and declaration text
DP-04 | Data Subject Rights | Subject Access Request (DSAR) workflow | Endpoint to export all data held on a named individual within 30 days | ⬜ Not Started | Tech Lead | Apr 2026 | DSAR test — full data export |  | GDPR Article 15 — 30-day legal deadline
DP-05 | Data Subject Rights | Right to Erasure / Right to be Forgotten | Anonymise PII on request (replace with [ANONYMISED]) preserving financial totals | ⬜ Not Started | Tech Lead | Apr 2026 | Erasure test — PII removed, totals preserved |  | GDPR Article 17
DP-06 | Data Retention | Retention schedule configuration | HMRC: payroll 3 years, employment records 6 years, financial records 7 years | ⬜ Not Started | CFO | May 2026 | Retention policy document signed by DPO |  | UK GDPR storage limitation principle
DP-07 | Data Retention | Automated retention enforcement | Celery task: flag records past retention window for review / deletion | ⬜ Not Started | Tech Lead | May 2026 | Retention task test
DP-08 | Data Security | Field-level encryption for PII | Encrypt: NI numbers, bank account numbers, bank sort codes, donor addresses | ⬜ Not Started | Tech Lead | Apr 2026 | Encryption key management test |  | UK GDPR Article 32 — appropriate technical measures
DP-09 | Data Security | Data breach logging | Incident log: discovery date, nature, data affected, individuals notified, ICO reference | ⬜ Not Started | Tech Lead | Apr 2026 | ICO 72-hour notification drill |  | GDPR Article 33 — notify ICO within 72 hours
DP-10 | Third Parties | Data processing agreements tracking | Record DPAs with: Stripe, PayPal, Supabase, Anthropic, any email provider | ⬜ Not Started | CFO | May 2026 | Signed DPA copies |  | GDPR Article 28 — required for all data processors
DP-11 | ICO Registration | ICO registration status tracking | Organisation must be registered with ICO — annual fee — registration number | ⬜ Not Started | CFO | URGENT | ICO registration certificate |  | Most organisations holding personal data must register — fee £40–£2,900/yr
DP-12 | Privacy Notice | Privacy policy version tracking | Current version, date, link — referenced on donor forms and employee records | ⬜ Not Started | CFO | Apr 2026 | Privacy notice document |  | GDPR Article 13/14 transparency requirement
DP-13 | Data Mapping | Data inventory / Record of Processing Activities (RoPA) | Document what personal data is held, where, why, retention, legal basis | ⬜ Not Started | DPO / CFO | May 2026 | RoPA document |  | GDPR Article 30 — mandatory for most organisations

## P2_Charity
CHARITY COMMISSION & CIC — COMPLIANCE CHECKLIST
Annual return, SORP reporting, trustees, conflict of interest, CIC statement, gift aid registration
Regulatory Basis: Charities Act 2011 · Charity Commission CC3/CC19/CC29 · Companies Act 2006 (CIC) · HMRC Charities
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
CC-01 | Charity Commission | Annual Return filing tracking | Deadline in compliance calendar — must be filed within 10 months of year end | ✅ Complete | CFO | Live | Compliance calendar evidence
CC-02 | Charity Commission | Independent examiner review tracking | Deadline tracked — independent examination required for income <£1m | ✅ Complete | CFO | Live | Compliance calendar evidence
CC-03 | Charity Commission | Trustees' Annual Report (TAR) | Narrative TAR meeting Charity Commission requirements — activities, achievements, future plans | ⬜ Not Started | CFO | Jun 2026 | TAR reviewed by trustee board |  | AI narrative exists but not in structured TAR format
CC-04 | Charity Commission | Charitable objectives compliance | Record how each programme delivers against stated CIC/charitable objectives | ⬜ Not Started | CFO | Jun 2026 | Board approval of objectives mapping
CC-05 | Charity SORP | Statement of Financial Activities (SoFA) | SORP FRS 102 compliant SoFA — restricted, unrestricted, endowment columns | ⬜ Not Started | CFO | May 2026 | Independent examiner sign-off |  | Requires FA-08 (restricted fund accounting) to be built first
CC-06 | Charity SORP | Reserves policy document and enforcement | Documented reserves target (3–6 months), current level, variance explanation | ⬜ Not Started | CFO | Apr 2026 | Board resolution approving reserves policy |  | Cash runway shown but no formal policy
CC-07 | CIC Compliance | CIC Community Interest Statement | Annual statement: activities, beneficiaries, community benefit, assets locked | ⬜ Not Started | CFO | Jun 2026 | Filed with Companies House |  | Specific to CIC legal structure — filed alongside annual accounts
CC-08 | CIC Compliance | Asset lock compliance tracking | Record confirming no distributions to shareholders — asset lock status | ⬜ Not Started | CFO | Jun 2026 | Companies House confirmation |  | Fundamental to CIC legal status
CC-09 | Governance | Conflict of interest register | Trustee/director conflicts declared, date, action taken, resolution | ⬜ Not Started | CFO | Apr 2026 | Board signed register |  | Charity Commission requirement — CC29 guidance
CC-10 | Governance | Trustee / director register | Full register: name, appointed date, resigned date, role, Companies House reference | ⬜ Not Started | CFO | Apr 2026 | Companies House match
CC-11 | Governance | Related party transaction register | All financial transactions with trustees or connected persons disclosed | ⬜ Not Started | CFO | May 2026 | Board approval + notes in accounts |  | Charity Commission CC29
CC-12 | Governance | Gift Aid HMRC Charities registration | Charity registered with HMRC to claim Gift Aid — charity reference number | ⬜ Not Started | CFO | URGENT | HMRC charity authorisation letter |  | Required before any Gift Aid claim can be made

## P2_Security
DATA SECURITY & CYBER — COMPLIANCE CHECKLIST
Authentication hardening, immutable audit trail, 2FA, encryption, Cyber Essentials, pen test
Regulatory Basis: UK GDPR Article 32 · ISO 27001 · Cyber Essentials Scheme · NCSC guidelines
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
SEC-01 | Authentication | bcrypt password hashing | All passwords hashed using bcrypt via passlib — no plain text storage | ✅ Complete | Tech Lead | Live | Code review
SEC-02 | Authentication | JWT authentication (24hr expiry) | JWT tokens with 24-hour expiry, signed with ALGORITHM = HS256 | ✅ Complete | Tech Lead | Live | Code review
SEC-03 | Authentication | Role-based access control (5 roles) | CFO, Finance Manager, Programme Manager, Admin, Viewer | ✅ Complete | Tech Lead | Live | Code review + test results
SEC-04 | Authentication | Session revocation (JWT blacklist) | Redis-backed token blacklist — invalidate tokens on logout or deactivation | ⬜ Not Started | Tech Lead | Apr 2026 | Logout invalidation test |  | Without this, terminated employee tokens remain valid until expiry
SEC-05 | Authentication | Rate limiting on login endpoint | Max 5 failed attempts per IP per 15 minutes — brute force protection | ⬜ Not Started | Tech Lead | Mar 2026 | Brute force test
SEC-06 | Multi-Factor Auth | Two-factor authentication (TOTP) | TOTP-based 2FA using pyotp — mandatory for CFO and Finance Manager roles | ⬜ Not Started | Tech Lead | Apr 2026 | 2FA enrolment and login test |  | HMRC and Charity Commission recommend MFA for financial systems
SEC-07 | Audit Trail | Immutable audit log model | AuditLog table: user, action, entity, field changed, old/new value, IP, timestamp — append only | ⬜ Not Started | Tech Lead | Apr 2026 | Audit trail test — no records editable or deletable |  | Required by HMRC, Charity Commission, and ISO 27001
SEC-08 | Audit Trail | Middleware logging all state changes | Every POST/PUT/PATCH/DELETE writes to audit log with before/after values | ⬜ Not Started | Tech Lead | Apr 2026 | Audit trail completeness test
SEC-09 | Data Security | HTTPS enforcement at application level | HTTPS redirect, HSTS headers, no plain HTTP access | 🔄 In Progress | Tech Lead | Live | Security headers test (securityheaders.com) |  | Configured at Vercel/deployment — not enforced in app
SEC-10 | Data Security | API key rotation tracking | Track all external API keys (Anthropic, Stripe, HMRC) with rotation schedule | ⬜ Not Started | CFO | May 2026 | Key rotation log
SEC-11 | Data Security | Sensitive field encryption at rest | NI numbers, bank details encrypted using sqlalchemy-utils EncryptedType | ⬜ Not Started | Tech Lead | Apr 2026 | Database inspection — fields not readable in plain text |  | UK GDPR Article 32
SEC-12 | Compliance Certification | Cyber Essentials certification | UK government-backed scheme — required by many grant funders | ⬜ Not Started | CFO | Jun 2026 | Cyber Essentials certificate |  | £300–500 for basic certification — increases fundability
SEC-13 | Compliance Certification | Penetration test (annual) | Professional pen test of the running application | ⬜ Not Started | CFO | Sep 2026 | Penetration test report |  | Best practice for financial software handling PII
SEC-14 | Business Continuity | Backup and disaster recovery plan | Documented backup schedule, Recovery Point Objective (RPO), Recovery Time Objective (RTO) | ⬜ Not Started | Tech Lead | May 2026 | DR test — restore from backup
SEC-15 | Data Security | CORS configuration (production hardened) | Restrict allowed origins to production domains only in non-development environments | 🔄 In Progress | Tech Lead | Apr 2026 | CORS header test in production |  | Currently allows *.vercel.app — tighten for production

## P1_Grants
GRANT MANAGEMENT — COMPLIANCE CHECKLIST
Grant portfolio, allocations, spending tracker, report generation, funder templates, outcomes
Regulatory Basis: NLCF Grant Conditions · GMCA Grant Agreement · Rochdale Council SLA · Charities SORP
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
GR-01 | Grant Management | Multi-grant portfolio management | NLCF, GMCA, Rochdale SLA — separate records with status, funder, amounts | ✅ Complete | CFO | Live | System demonstration
GR-02 | Grant Management | Grant allocation per programme/activity | GrantAllocation model — budget split across programmes | ✅ Complete | Tech Lead | Live | Code review
GR-03 | Grant Management | Real-time spending tracker | GrantSpending updated on expense approval — amount_spent on Grant record | ✅ Complete | Tech Lead | Live | Spending reconciliation test
GR-04 | Grant Reporting | Report deadline alerts | Celery task: alert CFO when grant report due within 14 days | ✅ Complete | Tech Lead | Live | Alert email test
GR-05 | Grant Reporting | AI-generated grant report narrative | Claude API generates narrative report from spending data | ✅ Complete | Tech Lead | Live | Sample report review
GR-06 | Grant Reporting | Funder-specific report templates | Templates matching NLCF, GMCA, Rochdale SLA reporting requirements | ⬜ Not Started | CFO | May 2026 | Funder acceptance of report format |  | Currently generic AI narrative — needs funder-specific structure
GR-07 | Grant Compliance | Grant conditions tracking | Conditions field per grant with compliance status | 🔄 In Progress | CFO | Apr 2026 | Conditions documented in system |  | Field exists — needs UI and workflow
GR-08 | Grant Compliance | Restricted fund code enforcement | Prevent charging ineligible expenses to a restricted grant | ⬜ Not Started | Tech Lead | May 2026 | Expense rejection test on wrong grant code |  | Requires fund accounting (FA-08) to be built first
GR-09 | Pipeline | Grant pipeline management | Prospect grants tracked with EOI status, application dates, decision dates | 🔄 In Progress | CFO | Apr 2026 | Pipeline data in system |  | Data exists statically — needs dynamic management
GR-10 | Outcomes | Outcome and KPI tracking | Link programme outcomes (participants, activities) to grant KPI requirements | ⬜ Not Started | CFO | May 2026 | Outcome data matching grant agreement |  | Required for NLCF and GMCA interim reports
GR-11 | Reporting | Volunteer hours valuation | 1,240 hours × £15.60 NCVO rate = in-kind match contribution | ✅ Complete | Tech Lead | Live | Volunteer value in reports
GR-12 | Compliance | Cost per beneficiary reporting | Spend / participants per programme — key funder metric | ✅ Complete | Tech Lead | Live | Per-programme cost reports

## P2_Donations
DONATION MANAGEMENT — COMPLIANCE CHECKLIST
Donor CRM, Gift Aid, Stripe/PayPal, recurring donations, GDPR consent, public donation page
Regulatory Basis: HMRC Gift Aid · UK GDPR · Payment Card Industry (PCI-DSS) · Fundraising Regulator Code
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
DON-01 | Donor Management | Donor CRM with contact records | Name, email, address, phone, source, anonymity flag | ✅ Complete | Tech Lead | Live | Code review
DON-02 | Gift Aid | Gift Aid eligibility tracking | Boolean flag per donor | ✅ Complete | Tech Lead | Live | Code review |  | Needs upgrading — see DON-03
DON-03 | Gift Aid | Gift Aid declaration audit trail | Declaration date, method, text version, withdrawal date — for HMRC audit | ⬜ Not Started | Tech Lead | Apr 2026 | HMRC Gift Aid audit readiness |  | Currently only boolean — HMRC requires full declaration evidence
DON-04 | Gift Aid | Gift Aid R68 claim submission | Online claim to HMRC ChAR — total donations, Gift Aid amount, charity reference | ⬜ Not Started | CFO | Apr 2026 | HMRC confirmation of claim |  | Manual via HMRC portal is acceptable — add tracking
DON-05 | Payments | Stripe payment integration | Payment intents, webhook processing for completed donations | ✅ Complete | Tech Lead | Live | Live transaction test
DON-06 | Payments | PayPal integration | PayPal client setup in settings — model support exists | 🔄 In Progress | Tech Lead | Apr 2026 | Live PayPal test transaction |  | Code structure present — needs live PayPal credentials and test
DON-07 | Payments | Recurring donation management | Recurring donation model, frequency tracking, Stripe subscription link | ✅ Complete | Tech Lead | Live | Recurring donation test
DON-08 | Compliance | Donor GDPR consent management | Marketing consent date, method, version — withdrawal mechanism | ⬜ Not Started | Tech Lead | Apr 2026 | Consent audit trail |  | See DP-02
DON-09 | Compliance | Donation receipt emails | Automated receipt email to donor on donation completion | ✅ Complete | Tech Lead | Live | Receipt email test
DON-10 | Reporting | Donation income by campaign | Breakdown of donations per campaign for grant match reporting | ✅ Complete | Tech Lead | Live | Campaign report test
DON-11 | Reporting | Year-on-year donation trend | YoY comparison for trustee and Charity Commission reporting | 🔄 In Progress | Tech Lead | Apr 2026 | Report accuracy test |  | Dashboard shows trend — formal year-comparison report needed
DON-12 | Fundraising | Online donation page / embed | Public-facing donation page or embeddable widget | ⬜ Not Started | Tech Lead | May 2026 | Live donation page test |  | Currently backend only — no public-facing donation UI

## P3_UKVI
UKVI SPONSORSHIP LICENCE — COMPLIANCE CHECKLIST
Sponsor licence management, CoS tracking, absence monitoring, 10 reporting duties, audit pack
Regulatory Basis: UK Visas & Immigration Sponsor Guidance (Dec 2023) · Immigration Act 2014 · Immigration Rules
Total Items | ✅ Complete | 🔄 In Progress | ⬜ Not Started | % Complete
Ref | Category | Requirement | Detail / What is Needed | Status | Owner | Target Date | Evidence Required | Date Completed | Notes
UK-01 | Licence Management | Sponsorship licence status tracking | Licence type (A-rated/B-rated), expiry date, licence number, renewal dates | ⬜ Not Started | HR Manager | Jun 2026 | Home Office licence confirmation letter |  | Only required if organisation currently holds or plans to apply for licence
UK-02 | Worker Records | Sponsored worker record (CoS) | Certificate of Sponsorship number, assigned worker, occupation code, salary, visa type, expiry | ⬜ Not Started | HR Manager | Jun 2026 | CoS assignment confirmation
UK-03 | Worker Records | Right to Work check (pre-employment) | Document type, number, expiry, check date, recheck date — per sponsored worker | ⬜ Not Started | HR Manager | URGENT | RTW document copies + check log |  | See also HR-01 — applies to all workers not just sponsored
UK-04 | Worker Records | Visa expiry alerts | Alert 90, 60, 30 days before visa expiry to HR Manager and CFO | ⬜ Not Started | Tech Lead | Jun 2026 | Alert delivery test
UK-05 | Reporting Duties | Absence monitoring (10+ consecutive days) | Flag any sponsored worker absent for 10+ consecutive working days — report to UKVI within 10 working days | ⬜ Not Started | HR Manager | Jun 2026 | Absence flagging test |  | 10 UKVI reporting duties must be understood and implemented
UK-06 | Reporting Duties | Role/salary change reporting | Log any change to sponsored worker's job title, location, or salary — reportable within 10 working days | ⬜ Not Started | HR Manager | Jun 2026 | Change notification test
UK-07 | Reporting Duties | Sponsored worker left employment reporting | Log leaving date and reason — report to UKVI within 10 working days | ⬜ Not Started | HR Manager | Jun 2026 | Leaving notification test
UK-08 | Salary Compliance | Going rate validation for occupation code | Validate sponsored worker salary >= going rate for their SOC occupation code | ⬜ Not Started | HR Manager | Jun 2026 | Going rate check per worker |  | Skilled Worker minimum salary £38,700 or going rate — whichever is higher
UK-09 | Audit Readiness | Home Office audit pack generator | On-demand export of all required sponsor documents for a UKVI compliance visit | ⬜ Not Started | Tech Lead | Jul 2026 | Simulated audit pack completeness test |  | UKVI can visit with 48 hours notice
UK-10 | Record Keeping | Sponsor record-keeping for 5 years | All HR records, right to work checks, CoS details retained for 5 years | ⬜ Not Started | HR Manager | Jun 2026 | Retention policy covers sponsored worker files |  | UKVI requirement — overlaps with data retention policy

## Implementation Roadmap
IMPLEMENTATION ROADMAP — COMPLIANCE DEVELOPMENT PLAN
Prioritised development plan to achieve full compliance across all regulatory domains
PHASE 1 — IMMEDIATE (Weeks 1–2) — Legal Liability Mitigation
Ref | Item | What to Build | Owner | Target | Notes | Status
PR-08 | NMW Validation | payroll_calculator.py — validate gross/hours >= NMW before run confirms | Tech Lead | Week 1 | CRIMINAL LIABILITY — top priority | ⬜ Not Started
HR-01 | Right to Work Records | Add RTW fields to Employee model + Alembic migration | Tech Lead | Week 1 | Criminal liability — illegal working | ⬜ Not Started
HR-03 | DBS Check Records | DBSCheck model + Celery renewal alerts | Tech Lead | Week 2 | Mandatory for youth organisation | ⬜ Not Started
SEC-04 | JWT Session Revocation | Redis token blacklist in get_current_user() | Tech Lead | Week 1 | 2 hours of work | ⬜ Not Started
SEC-05 | Login Rate Limiting | Add slowapi to requirements.txt, apply to /auth/login | Tech Lead | Week 1 | 30 minutes | ⬜ Not Started
PR-11 | P60 Generation | Extend ReportLab payslip — year-end certificate by 31 May | Tech Lead | Week 2 | Legal requirement | ⬜ Not Started
PR-12 | P45 Generation | Terminate employee endpoint + P45 PDF | Tech Lead | Week 2 | Legal requirement on leaving | ⬜ Not Started
PHASE 2 — MONTH 1 (Weeks 3–4) — GDPR and Data Protection
Ref | Item | What to Build | Owner | Target | Notes | Status
DP-11 | ICO Registration | Register with ICO if not already done | CFO | Week 3 | Annual fee £40–£2,900 | ⬜ Not Started
DP-01 | Lawful Basis Recording | Add lawful_basis field to data models with consent date | Tech Lead | Week 3 | UK GDPR Article 6 | ⬜ Not Started
DP-04 | DSAR Endpoint | POST /gdpr/subject-access-request — export all data for individual | Tech Lead | Week 4 | 30-day legal deadline | ⬜ Not Started
DP-05 | Right to Erasure | DELETE /gdpr/right-to-erasure/{id} — anonymise PII | Tech Lead | Week 4 | GDPR Article 17 | ⬜ Not Started
DP-08 | Field-Level Encryption | sqlalchemy-utils EncryptedType on NI, bank details | Tech Lead | Week 4 | UK GDPR Article 32 | ⬜ Not Started
SEC-06 | 2FA Implementation | pyotp TOTP — mandatory for CFO/Finance Manager | Tech Lead | Week 4 | 1 day of work | ⬜ Not Started
CC-12 | HMRC Gift Aid Registration | Register charity with HMRC to claim Gift Aid | CFO | Week 3 | Required before any Gift Aid claim | ⬜ Not Started
PHASE 3 — MONTH 2 — HR Module Build
Ref | Item | What to Build | Owner | Target | Notes | Status
HR-08 | Leave Management | LeaveRecord model + holiday/sick balance endpoints | Tech Lead | Month 2 | Working Time Regulations | ⬜ Not Started
HR-09 | Sickness Absence | Sick leave tracking + SSP trigger linkage | Tech Lead | Month 2 | SSP calculation dependency | ⬜ Not Started
PR-16 | SSP Calculation | calculate_ssp() in payroll_calculator.py — £116.75/wk | Tech Lead | Month 2 |  | ⬜ Not Started
PR-17 | SMP Calculation | calculate_smp() — 90% AWE then £184.03/wk | Tech Lead | Month 2 |  | ⬜ Not Started
HR-06 | Safeguarding Training Records | SafeguardingRecord model + expiry alerts | HR Manager | Month 2 | Statutory duty | ⬜ Not Started
HR-13 | Disciplinary Records | DisciplinaryCase model — confidential, audit protected | HR Manager | Month 2 | Employment Rights Act 1996 | ⬜ Not Started
SEC-07 | Immutable Audit Log | AuditLog model + middleware for all state changes | Tech Lead | Month 2 | Required for HMRC/Charity Commission audit | ⬜ Not Started
PHASE 4 — MONTH 3 — Financial Reporting Completeness
Ref | Item | What to Build | Owner | Target | Notes | Status
FA-08 | Restricted Fund Accounting | Fund model (restricted/unrestricted/endowment) + fund_id on all records | Tech Lead | Month 3 | Most impactful single addition | ⬜ Not Started
FA-10 | SoFA Report | SORP-compliant Statement of Financial Activities endpoint | Tech Lead | Month 3 | Depends on FA-08 | ⬜ Not Started
PR-15 | YTD Payroll Totals Fix | Calculate and populate ytd_gross, ytd_tax, ytd_ni on every PayrollRecord | Tech Lead | Month 3 | Existing bug — required for P60 | ⬜ Not Started
CC-09 | Conflict of Interest Register | Trustee model + ConflictOfInterest model | CFO | Month 3 | Charity Commission CC29 | ⬜ Not Started
CC-10 | Trustee Register | Trustee model with all required fields | CFO | Month 3 |  | ⬜ Not Started
FA-07 | Bank Reconciliation Lock | lock_date on BankAccount — prevent post-lock entries | Tech Lead | Month 3 | Required for clean audit | ⬜ Not Started
DP-06 | Data Retention Schedules | Retention config + Celery enforcement task | CFO | Month 3 | UK GDPR storage limitation | ⬜ Not Started
PHASE 5 — MONTHS 4–5 — UKVI + Advanced Compliance
Ref | Item | What to Build | Owner | Target | Notes | Status
UK-01 | Sponsorship Licence Tracking | Licence model with type, expiry, renewal dates | HR Manager | Month 4 | Only if licence held | ⬜ Not Started
UK-02 | Sponsored Worker / CoS Record | SponsoredWorker model linking to Employee | HR Manager | Month 4 |  | ⬜ Not Started
UK-05 | Absence Monitoring (UKVI) | 10-day absence flag + UKVI reporting duty alert | Tech Lead | Month 4 | 10-day rule — 10 working day report window | ⬜ Not Started
UK-09 | Home Office Audit Pack | On-demand export of all sponsor compliance documents | Tech Lead | Month 4 | 48-hour notice visits | ⬜ Not Started
PR-13 | P11D Generation | P11D model + PDF — benefits in kind | Tech Lead | Month 5 |  | ⬜ Not Started
PR-14 | IR35 Assessment Tool | IR35Assessment model + CEST reference tracking | CFO | Month 5 | For any contractor engagement | ⬜ Not Started
SEC-12 | Cyber Essentials Certification | Apply for Cyber Essentials — external assessment | CFO | Month 5 | Required by many grant funders | ⬜ Not Started